Shortening EIA Procedures for Power Plant Replacement
Abstract

Generally speaking, Replacements of aged thermal power plants lead to reduction of their environmental load (e.g. GHG emission, air pollutants, land development, etc.). Thus, such “load-reducing replacement projects” should be encouraged and accelerated from environmental point of view. However, the current EIA Law requires the same EIA procedures for such replacement projects as that of newly establishing projects, and there is an increasing demand in Japan for shorting the EIA procedures for power plants including these replacement projects, especially after the disastrous accident of the Fukushima Daiichi Nuclear Power Plant.
The Ministry of the Environment Japan published “Guideline for Streamlining EIA Methods on Thermal Power Plant Replacement” in March 2012, which enabled the project proponents to significantly reduce the duration necessary for survey and prediction in EIA process. Along with the guideline, measures to accelerate the reviewing process in the national and local governments were considered.

With all these efforts, the duration for EIA procedures, which normally takes about 3 years, is expected to be reduced up to 1 – 1.5 years.
Keywords：shortening EIA procedures, replacements of aged thermal power plants, load-reducing replacement projects, streamlining EIA methods
1. Background
When power generation replacements occur, aged  plants are mostly replaced by the newer, more efficient ones with cutting-edge technologies.
In such cases, replacement projects lead to reduction of their environmental load (ex. GHG emission, air pollutants, land development, etc.), as their environmental performances are improved and most of the thermal power plants are located in highly developed areas such as exclusive industrial zones or reclaimed lands.
Thus, such “load-reducing replacement projects” should be encouraged and accelerated from environmental point of view. However, the Environmental Impact Assessment Law (hereinafter referred to as “EIA Law”) requires the same procedures for these projects as required for those of new thermal power plants.
In addition, there is an increasing demand in Japan for shortening the EIA procedures for power plants including these replacement projects as almost all the nuclear power plants are shut down after the disastrous accident of the Fukushima Daiichi Nuclear Power Plant.
2. Guideline for Streamlining EIA Methods on Thermal Power Plant Replacement
The Ministry of the Environment (MOE) published “Guideline for Streamlining EIA Methods on Thermal Power Plant Replacement” in March 2012, which was revised in March 2013.

The guideline enables the proponents to implement assessments (especially survey and prediction) in a streamlined manner, and therefore, contributes to shortened EIA procedures.
2.1 Definition of Load-Reducing Replacement Projects
In this guideline, “load-reducing replacement projects,” to which the streamlined methods are applicable, is defined as follows:

1) Replacement projects that leads to the reduction of the following environmental loads:

· Emission of greenhouse gases calculated on the premise that the capacity factor remain unchanged after the replacement
· Emission of air pollutants - peak of hourly value
· Emission of aquatic pollutants - (peak of daily drainage) x (pollutants concentration)
· Discharge of heated water (cooling water) - (Increase in temperature) x (hourly heated water discharge)
2) Replacement projects of which ecological impacts caused by the land development are limited (e.g. the project is implemented within the premises of the existing plant or its adjacent area)
Even if a replacement project does not meet all of the requirements above, part of the streamlining methods below may be applicable to the project.
2.2 Basic Concept of the Guideline
For replacement projects, it is considered to be relatively easy for the project proponents to conduct surveys prior to the EIA procedure (e.g. survey of the habitat status of animals and plants). In addition, environmental monitoring data related to the operation of the existing plants is provided in many cases.

By preparing these data beforehand, the proponent can:
· Select the items to be considered in the EIA (evaluation items) and the assessment methods effectively and efficiently, and,
· Utilize the data to complement the results of the EIA, which will contribute to the streamlining.
2.3 Streamlined methods, etc.
The guideline specifies the streamlined methods for survey or prediction on each evaluation item, as well as the conditions, some of which are shown in Tables 1 through 4.
With these methods, survey and prediction duration may be shortened by 1 year or more, if all-year-round surveys become needless; such as animal and plants surveys.

Table 1: Streamlined methods on air quality
	Impact on air quality caused by exhaust gas

	(Requirements for streamlining)

· Exhaust emission and its concentration of air pollutants (hourly value and annual value) remain the same or decrease, and,
· Ground level ambient concentration (hourly value) remains stable or decreases. Etc.

	(Streamlined methods for survey etc.)

· Concentration measurement may be substituted with data at public air quality monitoring stations.
· Weather observation may be skipped. (using existing data)
· Simple comparison of ground level concentration before and after the replacement is applicable as prediction method.


Table 2: Streamlined methods on water temperature etc. and on marine life
	Impact on water temperature etc. and on marine life caused by heated water discharge

	(Requirements for streamlining)

· Heat emission* remain the same or decrease, and,
· Heated water outlet does not move beyond the range of 100 m, Etc.
* (Increase in temperature) x (hourly heated water discharge)

	(Streamlined methods for survey etc.)

· Simple comparison of water temperature etc. before and after the replacement is applicable as a prediction method.
· Survey of marine life may be skipped (using existing data). Etc.


Table 3: Streamlined methods on water quality
	Impact on water quality caused by pollutant discharge

	(Requirements for streamlining)

· Level of total nitrogen and total phosphorus as well as the COD (chemical oxygen demand) remain the same or decrease, and,
· Wastewater outlet does not move beyond the range of 300 m. Etc.

	(Streamlined methods for survey etc.)

· Water quality measurement may be skipped (using existing data). Etc.


Table 4: Streamlined methods on land animals and plants
	Impact on land animals and plants from land development etc.

	(Requirements for streamlining)

· Important species are not identified in the project implementation area (or its adjacent area), or,
· Green area within the project area does not change and the total area of habitats of the important species (other than green area) does not decrease, or,
· Habitat data of important species exists in the project implementation area. Etc.

	(Streamlined methods for survey etc.)

· Land animals and plants may be excluded from evaluation items,, or,

· Survey of land animals and plants may be skipped (using existing data). 


3. Shortening the Duration for Reviewing Process
In November, 2012, MOE and the Ministry of Economy, Trade and Industry (METI) published an “Interim Report on Shortening the EIA Procedures for Power Plants.” In this report, measures to shorten the EIA procedure are indicated, while maintaining the quality of EIA.
The two major aspects for shortening the EIA procedure are; (1) to utilize the Streamlining Guideline stated above and (2) to shorten the durations for the reviewing processes by related local and national governments.
The point is that the reviewing processes of the related local governments, METI and MOE are run parallel with close and earlier information exchange, while normally they are carried out by turns. (Pic. 1)
[image: image1.png]Draft of comments Comments

3—»-/ S

Comments

H M Draft of comments

omments P.roponen.t.s
view on citizens’
Submission and comments

disclosure of Draft EIS

e—— Conventional reviewing process

@=—p Streamlined reviewing process




Pic. 1: Concept of shortening the duration for the reviewing process
To achieve this, the following methods are stated in the report:
· METI reduces the number of consultation committees meetings,,
· METI prepares FAQs for smooth reviewing,

· METI requests project proponents to attend the consultation committees meetings if necessary for smooth reviewing,
· MOE reduces the duration for its own reviewing process and sends the draft of MOE comments to METI at an earlier stage in order to reflect it in the METI’s reviewing process,
· MOE and METI request the related local governments to share the information on the draft comments, in order to reflect them in their reviewing processes,
· MOE submits the final comments immediately after the comments from the local governments were submitted, and,
· METI, on condition that the draft comments were presented by the local governments by 1 week before the official submission, holds a consultation committee meeting immediately after the official submission of the comments, and makes its recommendation in about 3 weeks after the official submission of MOE comments.
With these efforts, the duration for the reviewing process of the national governments is expected to be shortened by 100 days at maximum. Also, further shortening is expected with close cooperation of local governments.
In contrast, however, each public comment period within the EIA procedures is untouched to ensure citizens’ opportunity to participate in the processes.
4. Conclusion

MOE, accepting the increasing demand of shorting the EIA procedures for power plants replacement, clarified the streamlining methods as the Streamlining Guideline that normally are responsibility of individual proponents, as well as measures to shorten the duration for reviewing process by the related governments. (Note: Under EIA Law, in Japan, it is project proponents’ responsibility to run the EIA. Therefore, scoping of each EIA is also proponents’ responsibility.)
With all the efforts stated in this paper, as well as other measures to shorten the EIA procedure indicated in the interim report, the duration for EIA procedures, which normally takes about 3 years, is expected to be reduced up to 1 – 1.5 years. These measures to shorten the EIA procedures can be applied to both ongoing procedures and future ones.
It should be reiterated that it is essential to maintain the quality of EIA while making such efforts to shorten the procedures. The guideline only recommends “omitting” each environmental impact only if that is ignorable, and also, public consultation procedure is untouched while governmental reviewing procedures are shortened.
1

